# Benedictine University Library Strategic Plan 2016-2019

# Guiding Principle #1: Create spaces that foster learning, creativity, ground-breaking research, and student success.

## Unify academic support units in one building.

    - Survey the current population of students, staff, and faculty to gather data on user needs and satisfaction in order to build a case for why we need a new library/spaces.  - University Librarian, Associate University Librarian, Branch Director Mesa (Fall 2016)

    - Work with stakeholders in each academic support unit/department to develop a vision of a unified academic support building.  - University Librarian (Spring 2017)

## Create a makerspace on the Lisle campus.

    - Conduct an environmental scan to identify existing maker equipment on campus and conduct a needs assessment. - Emerging Technologies Librarian (Fall 2016)

    - Secure permission to accept payment for special printing. - University Librarian (Fall 2016)

    - Identify and prepare a space for maker equipment. - University Librarian, Associate University Librarian (Spring 2017)

    - Develop a staffing plan, policies, and procedures. - University Librarian, Associate University Librarian, Emerging Technologies Librarian (Spring 2017)

    - Select and purchase equipment (3D printer, 3D scanner, plotter printer, computers, etc.) - Emerging Technologies Librarian (Summer 2017)

    - Train Library staff and student workers. - Emerging Technologies Librarian (Summer 2017)

## Enhance the technological infrastructure of our existing study spaces.

    - Add collaboration stations in open study spaces on the second floor of Kindlon Hall. - Associate University Librarian, Emerging Technologies Librarian (Summer 2016)

    - Add small collaboration stations in our study rooms. - University Librarian (Summer 2018)

    - Investigate the need for accessible workstations. - Associate University Librarian, Emerging Technologies Librarian (Summer 2018)

## Expand special collections space to include adequate storage for current collections and expected growth of the collections, designated processing space, and a reading room with space for researchers and displays.

    - Assess collection growth and anticipated 3, 5, and 10 year storage needs. - Archives and Special Collections Librarian (Spring 2016)

    - Add additional Archives storage space with appropriate environmental controls. - Archives and Special Collections Librarian, University Librarian (Summer 2016)

    - Add an Archives reading room that will accommodate use for researchers, displays, and small events. - Archives and Special Collections Librarian, University Librarian (Summer 2018)

    - Add designated processing space with areas for processing both physical and digital materials. - Archives and Special Collections Librarian, University Librarian (Summer 2018)

# Guiding Principle #2: Transform Library services to support the evolving needs of faculty & students throughout the lifecycle of scholarly communication.

## Transform reference and instruction services to include versatile formats to best serve all populations.

    - Integrate Library instruction and resources across all levels of the curriculum. -Outreach Librarians (Spring 2017)

    - Expand the web presence of all information literacy services, including embedding in classes, assignment development, and class-specific materials. - Outreach Librarians, Web Committee (Fall 2017)

    - Expand the use of online tutorials and workshops to increase usage of Library services and resources across all locations and online. – Reference and Outreach Librarians, Access Services Librarian. (Fall 2016)

    - Conduct a gap analysis of online services and resources. - Reference Librarians, Associate University Librarian (Fall 2016)

    - Establish a strategy for engaging with all distance stakeholders including administrators, students, faculty, adjuncts, instructional designers, and learning management system support teams. ­ All  (Spring 2017)

    - Increase access points for online learners to Library resources. - Digital Resources Librarian, Access Services Librarian.  (Fall 2017)

    - Explore alternative reference models with greater use of student workers on the reference desk. - Reference Librarians  (Fall 2017)

    - Transform reference services to a research consultation model. - Reference Librarians (Fall 2017)

    - Increase collaboration with faculty through workshops and one-on-one meetings, and faculty specific Research Guides. – Outreach Librarians (Spring 2017)

## Develop digital scholarship services.

    - Conduct a gap analysis of digital scholarship/scholarly communication services and conduct a needs assessment. - Emerging Technologies  Librarian, Digital Resources Librarian, Associate University Librarian (Fall 2016)

    - Develop skillsets needed to offer digital scholarship services. - Digital Resources Librarian, Emerging Technologies Librarian, Associate University Librarian (Spring-Summer 2017)

    - Offer workshops and/or consultations and Research Guides on digital scholarship/scholarly communication topics. (Fall 2017)

      - Open access and open educational resources - Copyright Committee

      - Data management - Science Outreach Librarian

      - Copyright and Creative Commons - Copyright Committee

      - Digitization and digital preservation - Archivists

      - Oral histories – Archivists

      - GIS and data visualization - Emerging Technologies Librarian, Science Outreach Librarian

      - Usability testing and technology evaluation - Emerging Technologies Librarian

      - Digital media assignments - Instruction Librarians, Emerging Technologies Librarian

      - Digital humanities projects - Digital Resources Librarian, Emerging Technologies Librarian

    - Host University publications that contain content generated primarily by Benedictine University students, faculty, or staff in Constellation. - Archives and Special Collections Librarian, Emerging Technologies Librarian (Fall 2017)

    - Host all student theses and dissertations in Constellation. - Archives and Special Collections Librarian (Spring 2018)

    - Create a web presence for digital scholarship services and showcase projects created with Library assistance on the Library website. - Web Committee (Summer 2017)

    - Promote digital scholarship services to faculty, staff, and students. - Community Relations Committee (Fall 2017)

## Make the University Archives the first stop for students doing primary source research.

    - Hire an Outreach Archivist. - University Librarian (Fall 2016)

    - Integrate Archives materials into courses across the curriculum, including non-history courses. - Archivists (Fall 2018)

    - Using DPLA’s model, develop Primary Source Sets for use in instruction/education. – Archivists (Spring 2017)

# Guiding Principle #3: Promote an active, visible, and vital presence in the academic life of the university.

## Collaborate with academic support units.

    - Invite the Student Success Center to offer tutoring in the Library for a few pre-determined hours each semester to reach more students. – Digital Resources Librarian (Fall 2016 and ongoing)

    - Contribute to the New Student Advising department’s retention efforts. – Digital Resources Librarian (Fall 2016 and ongoing)

    - Work with the Special Services Department to improve Library services and online and physical spaces for users with disabilities. – Digital Resources Librarian (Fall 2017)

    - Partner with the Center for Teaching and Learning Excellence on initiatives such as workshops, technology evaluation, Open Access Week events, adjunct orientations, and grants. – Emerging Technologies Librarian, Community Relations Committee (Fall 2016 and ongoing)

## Collaborate with student groups.

    - Establish a student advisory group for the Library. - University Librarian (Fall 2016)

    - Increase record donation from student organizations to the Archives. – Archivists, Digital Resources Librarian (Spring 2017)

    - Work with student groups to co-host events. - Community Relations Committee, Digital Resources Librarian (Spring 2017)

## Develop orientation for new students.

    - Identify opportunities for Library involvement in orientations to reach all student populations (Bridge to Success, Emerging Scholars, Athletics, and Transfer Orientation). – Digital Resources Librarian, Outreach Librarians (Fall 2017)

    - Develop, document, and implement a Library orientation plan that reaches all students, including a scavenger hunt or similar activity to engage students in the Library. – Digital Resources Librarian, Outreach Librarians (Summer 2018)

## Provide engaging programming.

    - Integrate Archives collections into CMI programs and endeavors. – Archivists (Spring 2017)

    - Partner with local organizations to hold public local history events. - Archivists, Community Relations Committee (Summer 2018)

    - Collaborate with academic departments to host topic and author events. - Community Relations Committee, Outreach Librarians (Fall 2018)

    - Offer low-tech and high-tech maker activities and small group workshops. - Community Relations Committee, Emerging Technologies Librarian (Fall 2017)

## Partner with Institutional Research to develop a comprehensive records management program and bring all departments/offices into compliance.

    - Conduct a survey of all records, paper and digital that are being created by the university.- Archives and Special Collections Librarian (Summer 2018)

    - Develop retention and disposition schedules that meet the needs of the university and are in compliance with all state and federal laws.- Archives and Special Collections Librarian (Fall 2018)

    - Coordinate with offices to ensure timely transfer of inactive records to the Archives and disposition of records with no enduring value.- Archives and Special Collections Librarian (Spring 2019)

# Guiding Principle #4:  Build and provide access to collections and services that support the mission of the University and all its units/programs.

## Improve discoverability of resources.

    - Form a Discovery System Task Force that will research and evaluate discovery systems and make formal recommendations to the Library Administration. – Associate University Librarian (Spring 2017)

    - Implement the discovery system selected by the Discovery System Task Force. - Digital Resources Librarian (Summer 2017)

    - Prepare for implementation of new ILS. - All (Summer 2016 and ongoing)

    - Reduce and eventually eliminate the processing backlog for Archives collections. - Archivists (Summer 2016 and ongoing)

    - Increase access to Archives collections by incorporating digitization and creation of CONTENTdm collections into regular processing procedures. - Archives and Special Collections Librarian (Fall 2017)

## Partner with related institutions, including St. Procopius Abbey, Sacred Heart Monastery, and Benet Academy to write finding aids for their hidden collections.

    - Identify partners/stakeholders at each organization. - Archives and Special Collections Librarian (Spring 2017)

    - Establish priorities and schedule for processing. - Archives and Special Collections Librarian (Summer 2017)

    - Develop cost-sharing mechanism for partners. - University Librarian, Associate University Librarian (Fall 2018)

    - Create finding aids. - Archivists (Spring 2018 and ongoing)

## Build rich and diverse collections.

    - Analyze interlibrary loan borrowing data to identify subject areas frequently requested and apply findings to collection development strategy. - Associate University Librarian (3 year cycle)

    - Continue to grow Archives and Special Collections with a focus on research collections. – Archivists

      - Update the current Collection Development Policy for the Archives and Special Collections. (Fall 2016)

      - Expand the scope of the oral history program to better document the Benedictine University Community. - Archivists (Spring 2017)

      - Incorporate record donation into retiring faculty off-boarding process.  University Librarian (Fall 2018)

    - Collaborate with the University Development to pursue collections from prominent alumni. - Archivists, University Librarian (Spring 2019)

    - Expand electronic resource collections beyond journals, books, and streaming videos; investigate and pursue specialized collections in support of the Benedictine mission.

## Take steps to better preserve Archives and Special Collections materials.

    - Develop and implement a digital preservation plan to supplement the Archives’ existing preservation plan. - Archivists (Spring 2017)

    - Address preservation and access issues by digitizing at-risk AV and high-use newspaper collections. - Archivists (Spring 2017)

    - Establish a budget for preservation activities. – University Librarian, Associate University Librarian, Archives and Special Collections Librarian. (Fall 2016)

    - Collaborate with facilities to stabilize the climate in Archives
storage space(s). - Archives and Special Collections Librarian (Fall 2016)

    - Pilot an Adopt a Book/Artifact program. - Archivists, University Librarian (Fall 2018-Spring 2019)

# Guiding Principle #5: Cultivate a climate of assessment.

## Define service standards.

    - Develop a checklist for planning instruction sessions to ensure consistency of instruction. - Outreach Librarians (Summer 2017)

    - Develop a checklist for providing reference to ensure consistency of reference interviews. - Reference Librarians (Summer 2017)

    - Develop a checklist for academic and non-academic liaison responsibilities to ensure consistency of Library presence. - University Librarian, Associate University Librarian (Summer 2017)

## Assess our impact by applying a user-centered, evidence-based approach.

    - Develop assessment standards and a timeline for each new initiative that will be used to determine if the project should be continued as is, adjusted to better meet the established goals, or discontinued. - Project Leads/Coordinators, Associate University Librarian (Summer 2018)

    - Conduct annual usability testing of the Library website. - Web Committee (Fall annually)

    - Monitor user experience and user research strategies and best practices and encourage Library staff to put them into practice where applicable. - Emerging Technologies Librarian, Digital Resources Librarian (Summer 2016 and ongoing)

    - Every other year, conduct a university-wide assessment survey. - University Librarian (Fall 2016 and Fall 2018)

## Practice open communication.

    - Implement a way for staff to communicate new ideas to Library Administration. - University Librarian (Spring 2017)

    - Evaluate the current committee and functional group structures with input from all stakeholders. – Associate University Librarian (Summer 2017)

## Ensure that all staff has adequate training to be at the cutting edge of the field.

    - Establish a schedule for regular peer-to-peer staff training that includes staff from all campus locations. - University Librarian, Associate University Librarian, Emerging Technologies Librarian (Summer 2016)

    - Identify core competencies for student workers and establish a training schedule. - Circulation Manager, other student hiring managers (Summer 2016)